## Sheet1
number | task | time taken (weeks) | deadline | support
1 | Create logo for yogo walk | 2 | 2025-11-29 | solomon
2 | Create wireframe sketches for home page, explore page, activity page | 1
3 | Implement app components (map, tracking, goals, yoga pose library) | 2
4 | Identify needed app components (map, tracking, goals, yoga pose library) | 1
5 | Research how Strava tracks user movement (GPS, speed, mapping APIs) | 1
6 | Create mock user activity cards (similar to Strava feed) | 1
7 | Draft content for Yoga pose list (Tadasana, Padmasana, Virabhadrasana etc) | 1
8 | Generate 4-frame pose animations for key poses | 2
9 | Imlement location based on user | 1
10